## Physical Report
DFID SWASTH (Department for International Development - Sector Wide Approach to Strengthening of Health)
Physical Progress upto 30/09/2014
S. No. | Name of Activities | Physical Target |  | Achievement | Remarks
1 | Model WATSAN Complex - Phase I | In Primary & middle School in 10 Districts | 100 | 43 | Work In Progress
2 | Model WATSAN Complex - Phase II | In Primary & middle School in 10 Districts | 100 | ____ | In the process of Tender disposal
3 | Solar M.S.W. Pump - Phase I | In 4 Block of Gaya District | 100 | 9 | Work In Progress
4 | Blanket Testing Drinking Water | Testing of Arsenic, Fluoride & Iron | 401010 | ____ | Work In Progress
5 | Mobile W. Q. Testing Lab. | Water Sample Testing | 12000 | 5502 | Work In Progress
6 | Strengthening of Dist. W. Q. Testing Lab. | All District Labs | 38 | 38 | Equipments and Chemicals have been supplied
7 | Rural Water Supply scheme | District - Purnia, West Champaran, Kisanganj, Nalanda & Gaya | 5 | ____ | Tender Disposal in Progress